Select any team name you prefer.
Please enter your name as it appears in Blackboard.
This is the priority ranking for this feature, relative to all other features.

Lower integers are higher in prioirty.

The customer may add or (for unimplemented features) remove features and change priority rankings at the start of each sprint.
This is the sprint during which the grader will grade your implementation of this feature.

By the END of this sprint, you must have implemented this feature.

If this field is blank, then this is a bonus feature. If implemented, it will be graded after the final sprint for extra credit.
This is the professor's estimate as to the relative difficulty of this feature in "points".

Points are unitless, and only have meaning relative to other estimates (a 2 point feature is expected to take about twice as long as a 1 point feature).

In a real project, points are assigned via a game of "estimating poker" played by the entire team.
Select the sprint number (1, 2, etc.) in which you plan to implement this feature. This is just for planning purposes, it won't affect your grade.

In Scrum, you only plan the current sprint, not future sprints, so you don't need to fill this in for any features not planned for the current sprint.

If you planned a "full credit" feature for the current sprint but don't complete it, then just update this cell for the next sprint. This will only affect your grade if this feature was *required* to be completed by a specific sprint, and is not.

If you planned a "bonus" or "extreme bonus" feature for the current sprint but don't complete it, and you don't want to use it for the next sprint, just use the Delete key to leave this cell blank. Your "full credit" grade will not be penalized for this decision.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Leave blank initially (hint: Use the Delete key)
Select "In Work" when you begin designing and coding this feature.
Select "In Test" when this feature is fully coded and you are testing it.
Select Finished ONLY when the feature works well and is READY TO SHIP.
    "Finished in Sprint 1" means it was delivered at the end of Sprint 1.
    "Finished in Sprint 2" - "Finished in Sprint 6" are the same for those sprints.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Please enter 2 or 3 capital letters that will represent you in the "Assigned To" column on each Sprint Backlog tab of this spreadsheet.
Please enter your UTA student ID number.
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help to User" feature, you might assign a Feature ID of "HELP" on the Product Backlog. Then, in the Sprint Backlog table, you might have 3 rows of tasks with Feature ID of Help - "Write help text", "Create help class to display help", and "Update CLI to accept '?' command".

COPY the status cell from row 1 for each row that you add, so that you can select its status with a drop-down. This will ensure that the Sprint Burn Chart at the top updates itself automatically as you complete your tasks.
Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for each task the agree to perform. Use this to ensure that no duplicate work occurs, and that no tasks "fall through the cracks".

If you are wroking individually, you do NOT need to put your initials next to every task. We'll figure out who did the work. Somehow.
Select a Feature ID to the left. Then, in this column, list each discrete task needed to implement that feature.

Example tasks might be "create the Foo class", "add the Bar method to the (existing) Qux class", "Find icons for the task bar", "Update the manual to cover this feature", or "Fix the seg fault bug".

Expect roughly 3 to 10 tasks per typical feature. Don't OVER plan, but also don't just write "Implement the feature". Find a middle ground. :-)
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
## Product Backlog
Product Name:	JADE Manager					Complete Fields in Green!!!
Team ID:

	Team Member Name					Initials	Student ID
Required

Sprint #	Remaining	Completed This Sprint			Comment
0	32			Total	Total number of features (in column H)
1	28	4		1	Total features left at the end of Sprint #1
2	25	3		2	Total features left at the end of Sprint #2
3	22	3		3	...and so on
4	20	2

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student but must be approved by the Product Owner in writing
				Sprints
Feature ID	Priority	Required	Est	Planned	Status	As a...	I want to...	So that I can…	Notes
CF	1	1	13	1	Finished in Sprint 1	Manager	Create a new coffee flavor	Stock and sell coffee products
CC	2	1	5	1	Finished in Sprint 1	Manager	Create a new donut	Stock and sell donuts
GUI	3	1	8	1	Finished in Sprint 1	Manager	Use a main window (GUI) with minimal menu bar only	Reduce training costs	This is the main window, with just a menu bar (for now). For this sprint, you can just hard-code or randomly create java and donuts
PS	4	1	5	1	Finished in Sprint 1	Customer	List the coffee and donut products in a dialog	See what is available (and later, see what the Customer can order)	This is effectively a string stream to a dialog with an OK button
IGUI	5	2	13	2	Finished in Sprint 2	Manager	Use dialogs to create new coffee and donut products	Reduce training costs	One dialog each for coffee and for donuts
BB	6	2	5	2	Finished in Sprint 2	Server	Use a button bar in the main window for common actions	Access features more quickly
CB	7	2	8	2	Finished in Sprint 2	Server	Create a new beloved customer (name AND phone#)	Keep track of our customers	Validate the phone number using Regular Expressions!
CO	8	3	8	3	Finished in Sprint 3	Server	Create an order of multiple products	Serve everyone in a customer party	Use “customer 0” for now, will select a customer later
POC	9	3	3	3	Finished in Sprint 3	Customer	Show the products in an order for the customer (what was ordered / how much it costs)	Verify that my order was taken correctly and see the price	This can simply be text in a MessageDialog, or something snazzier; probably similar to and maybe identical to Feature PS
CSB	10	3	8	3	Finished in Sprint 3	Customer	Associate the order with a customer	Self-order and not have to deal with people	“What name should I put on the ticket” so they can call for you when your order is ready. Associate these using a map or multimap. (Note: Because these are ordered containers, you may need to define operator< for your key!)
CE	11	4	5	4	Finished in Sprint 4	Manager	Maintain and display a cash register for the store	Manage the store’s finances	This should be displayed on the right of the status bar (add one if you don’t have one yet), or a similar constantly-visible location
MST	12	4	13	4	Finished in Sprint 4	Manager	Manage the state of each order (unfilled -> filled and unpaid -> paid, or unfilled / unpaid -> canceled)	Ensure each order is filled and payment collected	When an order is paid, add the difference between the price and cost to the cash register. If a paid order is canceled, reverse the credit.
SAVD	13		8			Manager	Save all data to a default file on exit or command	Ensure our data isn’t lost
LOAD	14		5			Manager	Load data from a default file on startup	Ensure our data isn’t lost
CM	15		8			Owner	Create roles with (simple) logins that change the GUI	Allocate responsibilities to my team	Support roles Owner, Manager, Server, and Customer, with a fixed password per role (or no login at all if you like for now). When switching roles, reconfigure menu / tool bar per UI Design. Don’t display the cash register value for the Customer role.
PIX	16		21			Customer	Add and display pictures for each item	Better understand the menu
POS	17		5			Server	Show the products in an order for the servers (what to prepare)	Know what to put into each serving in an order	This can simply be text in a MessageDialog, or something snazzier such as in the main window; probably similar to PS
P&L	18		8			Manager	Add a Profit & Loss statement, showing all income, expenses, and total profit	Ensure that we’re making a profit and thus avoid bankruptcy	This should be displayed by default for Owner role in the main window’s data area (as a table or Gtk::Label), right below the tool bar and above the status bar, if you have one.
AI	19		8			Server	Restock donuts and coffees	Ensure we can fill every order	This means keeping track of the quantity of each Product that’s at the counter, and when low, a Server can bring more from stock
RI	20		5			Manager	Display an Inventory Report, listing every item and the quantity in stock	Ensure we don’t run out of any product and thus disappoint our customers	This should be displayed by Server, Owner, or Manager request in the main window’s data area (as a table or Gtk::Label), right below the tool bar and above the status bar, if you have one.
RO	21		8			Manager	Create an Order Report, showing all orders in Pending, Filled, or Paid state (but not Completed or Discarded)	Better manage our production process	This should be displayed by default for Server and Customer roles or by Owner or Manager request in the main window’s data area (as a table or Gtk::Label), right below the tool bar and above the status bar, if you have one.
RB	22		5			Manager	Display a Customer Report, listing all info about each customer including any pending orders	Better attract repeat customers and handle complaints	This should be displayed for Manager role or by Owner request in the main window’s data area (as a table or Gtk::Label), right below the tool bar and above the status bar, if you have one.
EF	23		8			Manager	Edit a product	Improve our data and keep it synced to reality
ROA	24		3			Manager	Add Order Report option to show completed as well as pending orders	Review our order history seeking patterns to understand how to improve efficiency and profit
SALL	25		5			Owner	Save all data to a specified file	Franchise my company
LALL	26		5			Owner	Load data from a specified file	Franchise my company
CENEW	27		13			Owner	Create a new franchise	Franchise my company
XI	28		21			Manager	Retire a product (no longer enable its selection for a new order, but keep in reports)	Remove items no longer offered from the menu
CS	29					Manager	Hire a NAMED server, and login by server name	Keep track of our employees
ASTO	30					Manager	Also associate a server with the order they fill	Keep track of our employee productivity
XT	31		13			Manager	Suspend a server (no longer allow their selection for an order	Remove team members who aren’t currently active from our drop-down lists (except reports)
XXT	32		5			Manager	Restore a server	Add a former team member tack into service
Product Backlog Burn Chart
Sprints
Features Remaining at end of Sprint

## Sprint 04 Backlog
Sprint #	#VALUE!		Complete Fields in Green!!!
Start on	#REF!		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	#REF!
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
Sprint Burn Chart
Days
Tasks